BEACON OF NEW BEGINNINGS

Empowering Communities. Restoring Dignity. Building Futures.

ename@beaconnewbeginnings.org  |  011233551710100

PILOT PHASE FRAMEWORK

BNB & The Brain and Sleep Medical Centre Ltd

90-Day Pilot Period  |  Start Date: _______________  |  End Date: _______________

PURPOSE

This Pilot Phase Framework establishes the terms, structure, and success criteria for a 90-day trial partnership between Beacon of New Beginnings (BNB) and The Brain and Sleep Medical Centre Ltd. It responds directly to The Brain and Sleep Medical Centre Ltd's proposal to introduce a pilot phase to assess operational alignment, referral volume, and financial sustainability before committing to a full partnership agreement.

At the end of the pilot period, both parties will conduct a formal review to determine whether to proceed to a full partnership under the Memorandum of Understanding.

PILOT OBJECTIVES

- Test the referral pathway and intake process in real operational conditions

- Validate client category definitions and payment arrangements

- Assess communication and coordination between both organizations' liaison teams

- Identify any gaps, friction points, or improvements needed before full partnership launch

- Build confidence and trust between both organizations through shared experience

PILOT PARAMETERS

Duration

90 days from the date of MOU signing. Pilot start date and end date to be recorded above.

Referral Volume

During the pilot, BNB commits to referring a maximum of 10 clients to The Brain and Sleep Medical Centre Ltd. Both parties agree this cap allows for meaningful assessment without overwhelming either organization's capacity. The cap may be adjusted upward by mutual agreement if both teams are satisfied with early progress.

Client Category Distribution

BNB will aim to include referrals from all three agreed client categories during the pilot:

| Category | Description | Target No. (Pilot) | Payment Source |
| --- | --- | --- | --- |
| Fully Paying | Client can meet full service cost | 3–5 clients | Client / Family |
| Partially Supported | BNB co-funds a portion; client contributes | 3–4 clients | Client + BNB donor funds |
| Exceptional Cases | Acute need, no financial capacity | 1–2 clients max | BNB donor funds (pre-approved) |

PAYMENT PROCESS DURING PILOT

- BNB will confirm the client's payment category on the referral form at the time of submission

- For partially supported clients, BNB will attach a written Payment Commitment Letter specifying the BNB contribution amount and payment timeline

- For exceptional cases, BNB will submit a written Exceptional Case Request to The Brain and Sleep Medical Centre Ltd's liaison for prior approval before the referral is processed

- No referral will proceed to service delivery until payment arrangements are confirmed in writing

- The Brain and Sleep Medical Centre Ltd will invoice BNB directly for any agreed BNB-funded portions

PILOT MILESTONE SCHEDULE

| Milestone | Activity | Responsible | Timing |
| --- | --- | --- | --- |
| Pilot Launch | MOU and Pilot Framework signed; liaisons confirmed | Both parties | Day 1 |
| First Referral | BNB submits first referral using agreed form and category | BNB | Within 7 days of signing |
| Mid-Pilot Check-In | Liaison call to review progress, flag issues, adjust if needed | Both liaisons | Day 45 |
| Referral Log Review | Both teams review shared referral log for accuracy and completeness | Both liaisons | Day 60 |
| Pilot Close Review | Formal review meeting; assess outcomes against objectives | Both parties | Day 90 |
| Partnership Decision | Both parties confirm full partnership or agree on modifications | Both parties | Within 14 days of pilot close |

PILOT REVIEW CRITERIA

At the 90-day review, both parties will assess the pilot against the following criteria:

| Criterion | Target | Assessment Method |
| --- | --- | --- |
| Referral process adherence | 100% of referrals follow agreed pathway | Referral log audit |
| Intake response time | Acknowledged within 3 business days | Referral log timestamps |
| Payment compliance | All payment arrangements confirmed before service delivery | Invoice and payment records |
| Client satisfaction | No unresolved complaints from referred clients | Feedback from both liaisons |
| Communication quality | No missed liaison contacts; issues escalated promptly | Meeting notes and email log |
| Exceptional case management | All exceptional cases pre-approved; no financial disputes | Case files and correspondence |

PILOT REVIEW MEETING AGENDA

The 90-day review meeting will follow this structure:

- Referral volume and category breakdown — how many referrals were made, by category

- Process review — what worked, what didn't in the referral and payment pathway

- Financial sustainability check — were payment arrangements honored? Any disputes or delays?

- Client outcome check-in — any known outcomes or feedback from referred individuals

- Liaison relationship review — communication quality, response times, ease of coordination

- Decision: proceed to full MOU, modify terms, or extend pilot

SIGNATURES

Both parties agree to the terms of this Pilot Phase Framework and commit to participating in good faith throughout the pilot period.

IN WITNESS WHEREOF, the parties have executed this agreement as of the date first written above.

BEACON OF NEW BEGINNINGS

Signed: _______________________________

Name:    Enam Egyir

Title:      Executive Director

Date:      ___________________________

THE BRAIN AND SLEEP MEDICAL CENTRE LTD

Signed: _______________________________

Name:    Patience Asamoah

Title:      General Manager

Date:      ___________________________