# Implementation Plan Timeline

This document summarizes the phased implementation plan for Beacon New Beginnings (2025-2026), covering five key operational phases designed to establish, pilot, and scale recovery and rehabilitation programs for survivors of abuse and homelessness in Ghana.

# Phase 1: Foundation & Legal Setup (Months 1–3)

• 1.1 Legal Registration & Compliance (Month 1–2) - GH₵25,000 ($1,650)

• 1.2 Partnership Development (Month 2–3) - GH₵15,000 ($1,000)

• 1.3 Initial Team Setup - GH₵30,000 ($2,000)

# Phase 2: Service Development (Months 4–6)

• 2.1 Trauma-Informed Counseling Services - GH₵45,000 ($3,000)

• 2.2 Vocational Training and Life Skills Programs - GH₵60,000 ($4,000)

• 2.3 Emergency Support Infrastructure - GH₵40,000 ($2,650)

# Phase 3: Pilot Operations (Months 7–9)

• 3.1 Service Delivery Launch - GH₵55,000 ($3,650)

• 3.2 Technology and App Enhancement - GH₵20,000 ($1,300)

• 3.3 Strategic Partnership Expansion - GH₵25,000 ($1,650)

# Phase 4: Scale & Sustainability (Months 10–12)

• 4.1 Program Expansion in Greater Accra - GH₵60,000 ($4,000)

• 4.2 Financial Sustainability and Revenue Generation - GH₵20,000 ($1,300)

• 4.3 Quality Assurance and Impact Measurement - GH₵15,000 ($1,000)

# Phase 5: Advanced Services & Future Planning (Months 13–15)

• 5.1 Advanced Service Development - GH₵80,000 ($5,300)

• 5.2 Kumasi Expansion Preparation - GH₵40,000 ($2,650)

• 5.3 Year 2 Strategic Foundation - GH₵25,000 ($1,650)