# BEACON OF NEW BEGINNINGS - PARTNERSHIP PROGRAM

## Week 1-4 Execution Summary & Document Index

Program Launch Date: Week of February 10, 2026

Your Role: Solo Implementation

Duration: 4 weeks of prep before full outreach begins

---

## WHAT YOU'VE JUST BEEN GIVEN

You have **5 detailed, ready-to-use documents** covering every step of your first month:

### DOCUMENTS CREATED:

1. **Week 1: Strategy Meeting Agenda** (Week_1_Strategy_Meeting_Agenda.md)

- Full meeting agenda (90 minutes)

- Pre-meeting prep

- Post-meeting action items

- All materials and templates

2. **Week 2: Impact Data Compilation Guide** (Week_2_Impact_Data_Compilation_Guide.md)

- How to gather all your current impact data

- Metrics to compile

- Survivor story templates (with consent protocols)

- Data organization for pitches

3. **Week 3 Part A: Partnership One-Pager** (Week_3_Partnership_One_Pager.md)

- One-page overview document for partners

- Printing guidelines

- Customization for different sectors

- Design and distribution checklist

4. **Week 3 Part B: Partnership Tiers & Agreement** (Week_3_Partnership_Tiers_and_Agreement.md)

- Complete 4-tier partnership framework (Bronze/Silver/Gold/Platinum)

- Detailed deliverables for each tier

- Full sample partnership agreement (ready to customize)

- Legal review guidance

5. **Week 4 Part A: Prospect List & Research** (Week_4_Prospect_List_and_Research_Template.md)

- Prospect research framework and template

- How to identify good prospects

- Sector-specific research guides

- Master prospect list starter (20 Ghana companies)

- Research checklist

6. **Week 4 Part B: Outreach Email Templates** (Week_4_Prospect_Outreach_Email_Templates.md)

- 11 ready-to-customize email templates

- Sector-specific versions (Banking, Telecom, Tech, Healthcare, NGO, Government, etc.)

- Follow-up email sequences

- Email writing checklist

- CRM tracking templates

---

## YOUR WEEK-BY-WEEK EXECUTION PLAN

### WEEK 1: STRATEGY & ALIGNMENT (Due: Friday Feb 14)

Goal: Get organizational alignment on partnership vision, authority, and success metrics

Tasks:

Schedule partnership strategy meeting with Enam and advisors

Distribute meeting agenda and pre-reading

Conduct 90-minute strategy meeting

Document all decisions (champion, authority, budget, metrics)

Send post-meeting email with confirmed decisions

Establish weekly check-in cadence

Deliverables:

Strategy meeting held

Partnership champion identified

Budget approved

Success metrics agreed

Board/advisor commitments documented

Materials You'll Use:

Week 1 Strategy Meeting Agenda document

Success Looks Like:

Clear decisions documented

Team aligned and energized

Partnership program authority clear

Timeline and targets agreed

---

### WEEK 2: DATA COMPILATION (Due: Friday Feb 21)

Goal: Compile all current impact data and survivor stories for use in partnership pitches

Tasks:

Gather app metrics (downloads, users, ratings)

Collect survivor impact stories (with consent)

Compile organizational data (team, budget, operations)

Research DV problem in Ghana (statistics, facts)

Identify unique value propositions

Compile media coverage (if any)

Organize all data into master "Impact Data Summary" document

Review and approve with Enam

Deliverables:

Master "Impact Data Summary" document (all sections)

3-5 anonymized survivor stories (confidential)

Visual assets folder (logo, app screenshots, etc.)

Team credentials and organizational overview

DV problem statement with sources

Competitive landscape summary

Materials You'll Use:

Week 2 Impact Data Compilation Guide document

Success Looks Like:

All impact data compiled and organized

3-5 powerful survivor stories ready to use

Master document ready for partnership pitches

Data accurate and Enam-approved

---

### WEEK 3: PARTNERSHIP FRAMEWORK & MATERIALS (Due: Friday Feb 28)

PART A: Partnership One-Pager

Goal: Create single-page partnership overview document

Tasks:

Draft one-pager (cover and back)

Include impact data from Week 2

Highlight partnership tiers and benefits

Include clear call to action

Design professionally (colors, logo, images)

Proofread carefully

Create PDF version

Print 100 copies (optional)

Upload to website

Deliverables:

One-pager (draft and final)

PDF version

Print files (if printing)

Sector-specific versions (3-4 variations)

Materials You'll Use:

Week 3 One-Pager document

---

PART B: Partnership Tier Framework & Agreement

Goal: Define 4 partnership tiers and create legal agreement template

Tasks:

Finalize 4-tier structure (Bronze/Silver/Gold/Platinum)

Define deliverables for each tier

Create partnership tier comparison table

Draft sample partnership agreement (legal)

Include NDA template

Include brand guidelines

Review with legal advisor (if budget allows)

Finalize all tier documents

Deliverables:

Partnership tier framework (detailed)

Sample partnership agreement

NDA template

Brand guidelines

Tier positioning language

Materials You'll Use:

Week 3 Partnership Tiers & Agreement document

Success Looks Like:

One-pager ready to distribute

Partnership tiers clearly defined

Agreement template ready to customize for each partner

All materials professional and legally sound

---

### WEEK 4: PROSPECT RESEARCH & OUTREACH (Due: Friday Mar 7)

PART A: Prospect Research

Goal: Identify and research 20 priority prospects, create master prospect list

Tasks:

Identify 20 target companies (use Ghana-specific list provided)

Research each prospect (CSR program, budget, decision-maker)

Complete research form for each prospect

Assign fit scores (1-10 scale)

Estimate partnership tier for each

Prioritize: HIGH/MEDIUM/LOW for outreach

Identify warm introduction sources

Create master prospect spreadsheet

Flag top 10 for immediate outreach

Deliverables:

Master prospect list (spreadsheet with 20 prospects)

Research forms (for top 10)

Warm introduction sources identified

Prospect prioritization (HIGH/MED/LOW)

CSR decision-maker contact information

Materials You'll Use:

Week 4 Prospect List & Research Template document

---

PART B: Outreach Email Creation

Goal: Prepare all outreach emails for prospect contact (send Week 5+)

Tasks:

Review all 11 email templates

Customize emails for your top 10 prospects

Create sector-specific versions (Banking, Telecom, Tech, etc.)

Draft follow-up email sequences

Proofread all emails

Set up calendar booking link (Calendly or similar)

Establish CRM/email tracking system

Prepare response email templates

Ready to send in Week 5

Deliverables:

10+ customized outreach emails

Calendar booking link active

Email tracking system set up

Follow-up email templates

CRM spreadsheet or software configured

Materials You'll Use:

Week 4 Prospect Outreach Email Templates document

Success Looks Like:

20 prospects researched and prioritized

Top 10 fully prepared for outreach

Emails customized and proofread

Ready to begin contact in Week 5

---

## YOUR WEEK 1-4 TIMELINE AT A GLANCE

| Week | Focus | Deadline | Deliverables |

| **W1** | Strategy & Alignment | Feb 14 | Meeting held, decisions documented, team aligned |

| **W2** | Data Compilation | Feb 21 | Impact data, stories, organizational overview |

| **W3** | Partnership Framework | Feb 28 | One-pager, tiers, agreement template, materials |

| **W4** | Prospect Outreach Prep | Mar 7 | Prospect list, research, emails ready, CRM set up |

| **W5+** | Begin Outreach | Mar 14+ | Send emails, schedule calls, begin conversations |

---

## CRITICAL SUCCESS FACTORS (WEEKS 1-4)

For Week 1:

Get real buy-in from Enam and board (not just "OK")

Clarify decision-making authority

Secure budget commitment

Set clear success metrics

For Week 2:

Be honest about impact data (even if small numbers)

Collect meaningful survivor stories (quality > quantity)

Get consent for all survivor stories

Organize data professionally

For Week 3:

Make one-pager visually appealing (not text-heavy)

Define partnership tiers clearly (not vague benefits)

Get legal review of agreement (or at least someone review it)

Test email templates before using

For Week 4:

Research prospects thoroughly (15-20 min per prospect)

Personalize outreach emails (not generic)

Set realistic targets (aim for 15-20% response rate)

Build tracking system early (CRM or spreadsheet)

---

## WHAT COMES NEXT (WEEK 5 AND BEYOND)

### WEEK 5: BEGIN OUTREACH

Send 10-15 warm introduction emails (highest priority)

Send 5-10 cold outreach emails

Track responses in CRM

Schedule first discovery calls

Prepare for first calls

### WEEK 6-8: DISCOVERY CONVERSATIONS

Conduct 15-20 discovery calls

Listen for interests and fit

Answer questions about Beacon

Gauge genuine interest

Document all information in CRM

### WEEK 8-10: PROPOSAL DEVELOPMENT

For interested prospects, develop customized proposals

Address specific concerns

Propose partnership model

Share impact data

Set up formal pitch meetings

### WEEK 10-12: PITCH PRESENTATIONS

Conduct formal partnership presentations

Show app and impact

Answer detailed questions

Begin negotiations on terms

Target first 2-3 partnerships signed

### WEEK 12-18: ONGOING OUTREACH & CLOSURES

Continue Tier 2 prospect outreach

Negotiate and close partnerships

Implement first partnerships

Track impact and outcomes

Build momentum for future partnerships

---

## HOW TO USE THESE DOCUMENTS

As you execute each week:

1. **Read the relevant document** (e.g., "Week 1 Strategy Meeting" for Week 1)

2. **Customize it to your situation** (fill in names, dates, numbers)

3. **Use templates provided** (meeting agendas, emails, forms, etc.)

4. **Follow the checklists** (step-by-step guide through the week)

5. **Complete deliverables** (by Friday of that week)

6. **Move to next week** (with completed deliverables ready)

Documents are:

✓ Detailed and comprehensive

✓ Customizable to your situation

✓ Ready to use (not just frameworks)

✓ Step-by-step (not overwhelming)

✓ Practical (not theoretical)

---

## KEY PRINCIPLES TO REMEMBER

### 1. **One Person Can Do This**

These documents are designed for solo execution. You don't need a big team or consultant.

### 2. **Start Small, Scale Up**

Focus Week 1-4 on preparation. Weeks 5+ on outreach. Don't try to do both at once.

### 3. **Quality Over Quantity**

Better to have 3 great partnerships than 10 mediocre ones. Do prospect research. Customize emails.

### 4. **Track Everything**

Use CRM (Pipedrive, HubSpot) or spreadsheet. Track every email, call, and conversation.

### 5. **Survivor First**

Every partnership must pass the "survivor dignity" test. Does this partnership help survivors? Does it exploit them? Be willing to walk away from money if ethics are compromised.

### 6. **Relationship Building**

This is not transactional. You're building relationships. Follow-ups matter. Regular communication matters. Trust matters.

### 7. **Transparency & Accountability**

Tell partners the truth about Beacon (impact, challenges, growth). Be transparent about how their money/help is used. Regular reporting matters.

### 8. **Momentum Matters**

Early partnerships create momentum. First 2-3 are hardest. Once you have them, others come easier. Celebrate early wins.

---

## COMMON CHALLENGES & SOLUTIONS

### Challenge 1: "I don't have all the impact data"

Solution: Use estimates. Note data gaps. Honest is better than inflated. "We estimate 300-500 survivors reached since launch, plan better tracking going forward" is fine.

### Challenge 2: "Nobody's responding to my emails"

Solution: Normal. Most people don't respond to cold emails. Get warm introductions (ask Enam and board to introduce you). Response rates improve 5-10x with warm intros.

### Challenge 3: "I'm running out of time/energy"

Solution: This is expected. Partnership development is a marathon, not sprint. It's OK if Week 4 tasks spill into early Week 5. Quality over speed.

### Challenge 4: "Partners are asking for lower prices than tiers"

Solution: Flexibility is OK. If someone offers GHS 40K (mid-range), that's fine. Better to have partner at lower tier than no partner. Can upgrade later.

### Challenge 5: "I don't know who the decision-maker is"

Solution: Call the main number and ask "Who handles CSR partnerships?" Most companies will point you to right person. LinkedIn is your friend.

---

## SUCCESS METRICS FOR FIRST MONTH

By end of Week 4, you should have:

Organizational:

Partnership champion identified

Decision-making process clear

Budget approved (even if phased)

Board/advisor commitments documented

Team aligned and excited

Materials:

Impact data compiled and organized

One-pager designed and finalized

Partnership tiers documented

Agreement template ready

Prospect list created (20 companies)

Outreach emails drafted and customized

CRM/tracking system set up

Momentum:

Weekly team check-ins happening

Clear timeline and targets

Energy and excitement about program

Ready to begin outreach Week 5

---

## FINANCIAL INVESTMENT SUMMARY (WEEKS 1-4)

Minimal cash required to get started:

| Item | Cost | Required? |

| Professional printing (one-pager, 100 copies) | GHS 50-100 | Nice to have |

| CRM software (Pipedrive, HubSpot free tier) | Free | Yes |

| Calendar booking (Calendly) | Free | Yes |

| Email (Gmail) | Free | Yes |

| Google Docs/Sheets (storage, spreadsheets) | Free | Yes |

| **Total Hard Cost** | **GHS 50-100** | **Very low** |

Time Investment (Rough Estimates):

Week 1: 10 hours (meeting + strategy)

Week 2: 12 hours (data compilation)

Week 3: 15 hours (materials development)

Week 4: 10 hours (prospect research + emails)

**Total: ~47 hours over 4 weeks** (12 hours/week average)

If you're working solo, this is very doable.

---

## HOW TO GET THE MOST OUT OF THESE DOCUMENTS

### Do's:

✓ **Customize everything** - Templates are starting points, adapt to your reality

✓ **Use checklists** - They keep you on track

✓ **Follow the timeline** - Each week builds on previous week

✓ **Track progress** - Use tracking sheets provided

✓ **Ask for feedback** - Have Enam review key materials before finalizing

✓ **Adjust as needed** - If something isn't working, pivot

### Don'ts:

✗ **Don't follow blindly** - These are guidelines, not rules. Use what works.

✗ **Don't try to do everything at once** - One week at a time.

✗ **Don't skip the research** - Personalized emails > generic blasts.

✗ **Don't ignore the survivor ethics** - Everything through dignity/consent lens.

✗ **Don't expect fast results** - Partnership sales takes time (2-4 months typical).

✗ **Don't give up after first rejection** - "No" is just "not yet."

---

## YOUR ACCOUNTABILITY SYSTEM

Weekly Check-In (Every Friday):

Review week's deliverables (did you complete them?)

Update Enam on progress

Flag any blockers or challenges

Confirm next week's plan

Monthly Review (End of Month):

Full review of Month 1 progress

Assess what worked, what didn't

Adjust strategy if needed

Plan Month 2 priorities

Use this template:

WEEKLY CHECKPOINT - [DATE]

Week Completed: [W1/W2/W3/W4]

Deliverables Completed: [List what's done]

On Track? [Yes/No]

Blockers or Challenges: [Any issues?]

Next Week's Plan: [What's coming]

Support Needed: [What help do you need?]

---

## ONE FINAL THING: YOU'VE GOT THIS

I want to be clear: This is a lot of work, but it's completely doable by one person.

These documents give you:

✓ Clear roadmap (week by week)

✓ Ready-to-use templates (not starting from scratch)

✓ Real examples (not just theory)

✓ Practical checklists (to keep you on track)

✓ Customizable materials (not generic)

You have everything you need. You don't need a consultant. You don't need a big team. You need to:

1. **Execute the weeks in order**

2. **Use the templates provided**

3. **Customize to your situation**

4. **Track everything**

5. **Keep moving forward**

The hardest part is actually starting. You're past that now.

Week 1 starts Monday. You've got this.

---

## DOCUMENT REFERENCE GUIDE

Need to find something? Use this guide:

| Need | Document | Section |

| Strategy meeting plan | Week 1 | Full document |

| Impact story template | Week 2 | Section 2 |

| Impact data checklist | Week 2 | Section 9 |

| One-pager template | Week 3A | Full document |

| Partnership tier details | Week 3B | Part 1 |

| Partnership agreement | Week 3B | Part 2 |

| Prospect research form | Week 4A | Section 2 |

| Ghana company list | Week 4A | Section 6 |

| Email templates | Week 4B | Templates 1-11 |

| Email checklist | Week 4B | Email Writing Checklist |

| CRM tracking template | Week 4B | Tracking section |

---

## YOUR NEXT STEP

Right now:

1. **Pick a start date** (Monday, Feb 10? Or following Monday?)

2. **Read Week 1 document** (full document - it's comprehensive)

3. **Schedule the strategy meeting** (on your calendar)

4. **Set a reminder** (Friday Feb 14 for deliverables)

5. **Email Enam** (let him know you're starting)

Then:

Execute Week 1

Complete deliverables by Friday

Move to Week 2

Repeat each week

You're ready. Let's build sustainable partnerships and change lives.

---

Remember:

Small wins build momentum

Perfect is the enemy of good

Imperfect action beats perfect planning

You're further ahead than you know

Now go execute. Week 1 starts Monday.

---

All documents prepared for: Enam Egyir / Beacon of New Beginnings

Partnership Program Start Date: Week of February 10, 2026

Created: February 10, 2026

Version: 1.0 - Ready to execute